## SharePoint Migration
ARRIS Technical Services SharePoint Spectrum Intranet Site Update
PROJECT START DATE | 2021-05-24
Project Summary Tasks | Priority | Start | Finish | Target Start Date | Target End Date | Duration | Status | % Complete | Task Owner | Task Resources | SP Site Business Owner | Notes
Project Kick Off |  | 2021-05-24 | 2021-07-15
Prepare Project Plan
Starlette send excel project tracker template to Cole |  | 2021-05-24 | 2021-05-24 |  |  | 1 day(s) | Completed | 100% | Starlette
Meeting to review template with Ann and Starlette |  | 2021-05-26 | 2021-05-26 |  |  | 1 day(s) | Completed | 100% | Cole | Starlette, Ann |  | Cole setup meeting 5/26.
Starlette send welcome for Cole |  | 2021-05-26 | 2021-05-27 |  |  | 2 day(s) | Completed | 100% | Starlette
Kick off communication introducing Cole and project |  | 2021-06-02 | 2021-06-03 |  |  | 2 day(s) | Completed | 100% | Ann | Cole |  | Ann to send communication to announce Cole here to assist with standardizing Tech Svcs SP sites.
Cole Creates Template for Business Owners |  | 2021-05-27 | 2021-06-04 |  |  | 7 day(s) | Completed | 100% | Cole
Discover, Analyze Sites |  | 2021-05-21 | 2021-06-04 |  |  | 11 day(s)
SharePoint training |  | 2021-05-17 | 2021-06-01 |  |  | 12 day(s) | Completed | 100% | Cole |  |  | Cole on going training
Inventory Audit - Tech Services SharePoint Site |  | 2021-05-25 | 2021-05-26 |  |  | 2 day(s) | Completed | 100% | Cole |  |  | Discovery: Produce An inventory of the non matching data items, including properties such as name size, date created and/or changed, file type, any metadata held. A list of processes, workflows, or rules that the organisation uses to manage the data. Prepare list matrix recording for each site what are non-conformance issues - Determine level of effort needed for each site that needs to be updated
SITE 1 Business Transformation & COE | [5 empty] | #VALUE! |  |  |  |  | Ann Goldsborough
Cole adds contact information |  | 2021-06-07 | 2021-06-07 |  |  | 1 day(s) | Completed | 100% | Cole
Contact Derek Miller about description for the SharePoint site |  | 2021-06-07 | 2021-06-07 |  |  | 1 day(s) | On Track | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Ann
Site Owner signs off on Changes |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
SITE 2 Tier 4 - INDA TS (Emailed) | [10 empty] | Prakash | Emailed (2) Times; Scheduled meeting. Said that he wanted to add some things to his site, but he will send an email of what it is that he wants.
Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-06-25 | 1 day(s) | Completed | 100% | Cole
Make the contact site a link |  | 2021-07-30 | 2021-07-30 | 2021-06-25 | 2021-06-25 | 1 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-06-28 | 2021-06-30 | 1 day(s) | Completed | 100% | Cole |  |  | Cole will send email today 8/3 to An nto review
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-01 | 2021-07-01 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-02 | 2021-07-02 | 1 day(s) | Completed | 100% | Cole |  |  | Site contact
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-02 | 2021-07-02 | 1 day(s) | Completed | 100% | Cole |  |  | If Ann able to get to approve and publish ETA 8/4
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-02 | 2021-07-02 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-03 | 2021-07-03 | 1 day(s) | Completed | 100% | Cole
SITE 3 VOD TS (Emailed) | [10 empty] | Christin & Chris Tooley | Currently waiting for fix for navigation bar
Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-06-16 | 2021-06-16 |  |  | 1 day(s) | Completed | 100% | Cole
Add contact site |  | 2021-06-16 | 2021-06-16 |  |  | 1 day(s) | Completed | 100% | Cole |  |  | Cole will send email today 8/3 to An nto review
Add Tech services and support to the navigation bar |  | 2021-06-16 | 2021-06-17 | 2021-06-16 | 2021-06-30 | 2 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole |  |  | Site contact
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole |  |  | If Ann able to get to approve and publish ETA 8/4
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 4 Advertising TS (Emailed) | [6 empty] | New TBA |  |  |  | Josh Kerley | Currently waiting for fix for navigation bar
Meeting for Communication to Business Owner/ Stakeholders: Content and shape of the data,Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
Add Tech services and support to the navigation bar |  | 2021-06-11 | 2021-08-02 |  |  | 37 day(s) | Completed | 100% | Cole |  |  | COLE needs to update project plan
Add contact site |  | 2021-06-11 | 2021-06-11 |  |  | 1 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | cole
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 5 Video Products & Services | [11 empty] | Send email on what to do with the site since it's blank
Meeting for Communication to Business Owner/ Stakeholders: Content and shape of the data,Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-07-08 | 2021-07-08 | 2021-07-06 | 2021-07-06 | 1 day(s) | Completed | 100% | Cole
Add contact site |  | 2021-07-28 | 2021-07-28 | 2021-07-13 | 2021-07-14 | 1 day(s) | Completed | 100% | Cole
Add Tech services and support to the navigation bar |  | 2021-07-28 | 2021-07-28 | 2021-07-14 | 2021-07-15 | 1 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | cole
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 |  | Completed | 100%
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 6 TAC (Emailed) | [10 empty] | Regina Faustine | Emailed 2 times. She comes back in office on 6/24/21. Ask Ann about what to do since they don't use their sharepoint site
Meeting for Communication to Business Owner/ Stakeholders: Content and shape of the data,Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-07-09 | 2021-07-09 | 2021-07-06 | 2021-07-06 | 1 day(s) | Completed | 100% | Cole
Add navigation bar |  | 2021-07-09 |  | 2021-07-13 | 2021-07-14 |  | Completed | 100% | Cole
Add logo to site |  | 2021-07-09 |  | 2021-07-13 | 2021-07-14 |  |  |  | Cole
Add Tech services and support to the navigation bar |  | 2021-07-09 |  | 2021-07-13 | 2021-07-14 |  |  |  | Cole
SME Reviews and Approvites Site Changes |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | cole
Site Owner signs off on Changes |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
Email Site Owner to Review Changes (2 Day Approval) |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
Publish changes |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | Cole
Send Email Saying Changes are Published |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
SITE 7 Consumer TS (emailed) | [10 empty] | Annette Kanakaris | Check with Ann about this site. Might not need to update this. (the're spinning off to another site). Contact cheryl poon about loading feature
Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-07-19 | 2021-07-19 | 2021-07-06 | 2021-07-06 | 1 day(s) | Completed | 100% | Cole
Add logo to site |  | 2021-07-20 | 2021-07-20 | 2021-07-13 | 2021-07-14 | 1 day(s) | Completed | 100% | Cole
Add contact site |  | 2021-07-21 | 2021-07-21 | 2021-07-13 | 2021-07-14 | 1 day(s) | Completed | 100% | Cole
Change the loading feature |  |  |  | 2021-07-13 | 2021-07-14 |  |  |  | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-14 | 2021-07-16 | 1 day(s) | Completed | 100% | cole
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 8 Video Products East TS (Complete) | [10 empty] | Wayne Bilardo | Emailed twice. Meeitng scheduled
Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-06-21 | 2021-06-21 |  |  | 1 day(s) | Completed | 100% | Cole
Add contact site |  | 2021-06-21 | 2021-06-21 |  |  | 1 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | cole
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 9 Contracts (Complete) | [10 empty] | Jim Morgan
Meeting for Communication to Business Owner/ Stakeholders: Content and shape of the data,Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-07-19 | 2021-07-19 | 2021-07-06 | 2021-07-06 | 1 day(s) | Completed | 100% | Cole
Make the contact site a link |  | 2021-07-27 | 2021-07-27 | 2021-07-13 | 2021-07-14 | 1 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | cole
Site Owner signs off on Changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Email Site Owner to Review Changes (2 Day Approval) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Publish changes |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
Send Email Saying Changes are Published |  | 2021-08-04 | 2021-08-04 | 2021-07-15 | 2021-07-16 | 1 day(s) | Completed | 100% | Cole
SITE 10 Global Knowledge Services (Complete but wants site redesign) | [10 empty] | Andrew Dahl | Wants a whole site redesign
Send email asking to have a meeting |  | 2021-07-09 | 2021-07-09 | 2021-07-06 | 2021-07-06 |  | Completed | 100%
Meeting with Business Stakeholders to communicate: Content and shape of the site, and what needs to change to meet standards |  | 2021-07-09 | 2021-07-09 | 2021-07-13 | 2021-07-14 | 1 day(s) | Completed | 100% | Cole |  |  | Cole's Notes on Site Design Changes They Want: Main products aren't following the look and feel of the regular sites Want description and want table of contents like the BTCOE site Want template to match Add site contact Add logo to site Wants two columns (one location for links) leave the links at the bottom products projects pools KEY: have lots of products and document libraries that need permissions; fix that networks and workassure release libraries should be folders Sent email to Andrew explaining that the changes were not made yet because his team was still working on the redesign
Change template to Office style |  |  |  | 2021-07-13 | 2021-07-14 |  | On Hold |  | Cole |  |  | Didn't want to change the template yet because I didn't want it to throw people off and lose track of where things were on the site
Add header to the SP site |  | 2021-07-13 | 2021-07-28 | 2021-07-13 | 2021-07-14 | 12 day(s) | Completed | 100% | Cole
Add contact site |  | 2021-07-13 | 2021-07-28 | 2021-07-13 | 2021-07-14 | 12 day(s) | Completed | 100% | Cole
Add Tech services and support to the navigation bar |  | 2021-07-13 | 2021-07-28 | 2021-07-13 | 2021-07-14 | 12 day(s) | Completed | 100% | Cole
SME Reviews and Approvites Site Changes |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | Cole
Site Owner signs off on Changes |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
Email Site Owner to Review Changes (2 Day Approval) |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | Cole
Send Thank You and Send Publish Date (Any day but Friday) |  |  |  | 2021-07-15 | 2021-07-16 |  |  |  | Cole
Publish changes |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
Send Email Saying Changes are Published |  |  |  | 2021-07-15 | 2021-07-16 | #VALUE! |  |  | Cole
Check in with Business for sign off
End of Project Communication
Communication to Tech Svcs - Changes have been completed to the SharePoint site
Formulas:
Duration = IF(OR([Start]=0,[Finish]=0),"",NETWORKDAYS([Start],[Finish])& " day(s)")
Duration = IF(OR([Start, row above]=0,[Finish, row above]=0),"",NETWORKDAYS([Start, row above],[Finish, row above])& " day(s)")

## Project Tracker Instructions
Excel Project Tracker - Guidance and Tips:
Type your own feature or task names and dates for each Sprint inside the table on the Excel Sprint Project Tracker sheet. The template's functions will automatically calculate the duration of each task and estimate how much each sprint will take to accomplish your goals.
The Gantt chart to the right of the Project tracker will auto-update whenever you change your tasks' dates or % Complete, or when you enter more items in the table.
To display a different time period on the timeline, change the numer next to SCROLL TO WEEK in the table.
To enter additional features or tasks, simply insert new rows within the table and type in your data.
The Excel Sprint Project Tracker lets you quickly add extra Sprints, complete with the functions that automate calculations and graphic updates. To do so, select and copy all rows correspoding to an existing Sprint section, right-click on the row where you want to include your new section, and then select Insert Copied Cells from the pop-up. Then, just replace the duplicated data with new information.
The color of the Gantt chart task bars can also be changed, by using Conditional Formatting. Select all cells corresponding to the Gantt chart, click the Conditional Formatting button on the Home tab, and then select Manage Rules. Here, choose the formula you wish to customize (Blue for Completed Tasks, Orange for Tasks in Progress), and then click on Edit Rule. This is where you'll find all customization options for the task bar formulas, including the option to change the Orange or Blue Fill color.
Changing Task Colors